Appendix 1:  Organisational Development (OD) Plan (23-26) Close Down Report

Introduction

In July 2023, the Board approved a 3-year (23-26) Organisational Development (OD) plan for the ICB. The aim of the plan is to support the delivery of the change programme by focusing on creating a healthy culture driven by strong values, high capability and effective relationships and ways of working that will enable the NCL ICB to adapt, perform and thrive now and in the future.

This report sets outlines the progress against phases one (23-24) and two (24-25) against the priority actions identified in the OD plan.

Background and Context

The OD plan is based on the evolved Culture and Leadership Programme based on best practice, developed by Professor Michael West and sponsored by NHSE which focuses on 6 key pillars:

- Vision and Values - An inspiring and shared vision and values that sets a clear direction and expectations; creating a strong identity and thriving culture that fosters pride and positivity.

- Goals and Performance - Clear priorities and objectives at every level and intelligent data informing all about performance. Recognising and rewarding good work and ensuring resources are available and used well.

- Learning and Innovation - Investing in opportunities for people to nurture, grow and improve how work gets done, ensuring fair and equitable access to learning, development, innovation and career progression.

- Support, Compassion and Wellbeing - Nurturing a compassionate and psychologically safe culture, where staff feel cared for, valued and respected and feel confident to raise concerns knowing they will be addressed.

- Equity and Inclusion - Equity, positive diversity, and comprehensive inclusion for all, where staff can bring their whole selves to work safe in the knowledge they will be valued and respected.

- Team and System Working - Effectively functioning team and inter-team working with role clarity, shared objectives, and cooperation; working collaboratively across organisations and systems.

The 3-year OD plan was developed in 2023, and the priorities and areas of focus were reflective of the needs of the staff and organisation at that point in time. Since the roll out of the OD plan in July 2023, there was a need to review the timescales for delivering the priorities in particular those priorities that required co-design and engagement with staff because it became clear that there would be low meaningful engagement from staff due to the impact of the change programme, transitioning to new ways of working and the new structure, and feedback from staff themselves on workload pressures. In view of these factors, the timescales of delivering some of the activities were paused to a later date.

As we moved forward from the 2023 organisational change programme, it was recognised that the needs of the staff and organisation changed and therefore it was agreed that going forwards the delivery areas against each of the pillars will be iterative and may need to change on an annual basis so it is responsive to staff feedback, engagement and needs.

We have just completed year/phase 2 of the 3-year OD plan. During 24/25, work progressed to meet the objectives in these six areas as part of the delivery plan.

Progress against the 3-year OD Plan

The organisational development plan is enabling the ICB to create a thriving and re-energised culture as part of the implementation of the new organisational structure. We have completed year/phase 2 of the 3-year OD plan. During 24/25, as part of the delivery plan, work continued to be progressed to meet the objectives in the six areas, and the following areas have been completed/achieved:

- Review and develop on-boarding and induction to reflect vision, values, structures and operating model for existing staff and managers following the redesign and for all new staff and managers

- Improve visibility of senior leadership across sites with staff at all levels of the organisation

- Design a process to ensure all job descriptions reflect the vision, values and operating model

- Regularly review and report on ER cases, including timeliness, variation and disparity; ensuring regular reviews/audits are completed and embed learning

- Design and deliver leading change programme to support managers and staff through change, transition and integration

- Review mandatory training requirements and reporting, monitoring processes following restructure

- Review communication channels and access to support staff to raise concerns

- Support staff with change process with access to immediate health and wellbeing support

- Develop and embed the role of the Wellbeing and Inclusion Guardian

- Complete Equality Impact Assessment (EQIA) of new structure and management of change process and continue to embed approach to sustain best practice

- Embed fair recruitment practices at all levels across the ICB

- Deliver change and transition sessions with teams to support operational and personal resilience during change programme

- Develop and implement a high performing team development programme for the newly established teams

Due to the forthcoming change programme, a decision has been taken to pause the requirements of delivering the OD plan and focus on supporting staff throughout the change programme with regards to wellbeing, careers support and fair and inclusive processes. A workforce strategy will be developed at the appropriate time in the future.

Progress update against the 3-year Organisational Development Plan

| Key Priority | Priority Actions | Lead | Actual/target completion date | RAG rating |
| --- | --- | --- | --- | --- |
| Vision and Values | Co-create a vision and values and behaviours framework, embedding our values and expected behaviours into all that we do | Corporate | Year 3 | Not yet started |
| Vision and Values | Establish a staff engagement and communication programme including regular pulse checks | Corporate | Year 2/3 | In progress |
| Vision and Values | Review and develop on-boarding and induction to reflect vision, values, structures and operating model for existing staff and managers following the redesign and for all new staff and managers | Corporate | Year 2 | Complete |
| Vision and Values | Improve visibility of senior leadership across sites with staff at all levels of the organisation | Directorate | Year 1 | Ongoing |
| Goals and Performance | Create a high-quality performance management and appraisal process aligned to the values and behaviours framework, which embeds the ICB vision and priorities | Service/Team | Year 2/3 | In progress |
| Goals and Performance | Design and embed a leadership competency and behaviours framework and assessment process aligned to the NHS Leadership compact, NCL ICB Values and Behaviours Framework and system programmes | Corporate | Year 2/3 | In progress |
| Goals and Performance | Design a process to ensure all job descriptions reflect the vision, values and operating model | Directorate | Year 1 | Complete |
| Goals and Performance | Regularly review and report on ER cases, including timeliness, variation and disparity; ensuring regular reviews/audits are completed and embed learning | Corporate and Directorate | Year 1/2 | Complete |
| Goals and Performance | Design and deliver staff recognition and celebration programme celebrating and sharing success | Corporate | Year 2/3 | Not yet started |
| Goals and Performance | Establish and embed a talent management approach and practice | Corporate | Year 3 | Not yet started |
| Goals and Performance | Establish a systematic succession planning process for business-critical roles | Corporate | Year 3 | Not yet started |
| Learning and Innovation | Continue to invest in tailored leadership and management development that embeds our vision, values and leadership competencies - create a menu of interventions and offers including access to coaching and mentoring | Corporate | Year 2/3 | In progress |
| Learning and Innovation | Upskill managers with HR and finance information, policies, procedures, and good practice in line with new structures and operating model | Directorate | Year 2/3 | In progress |
| Learning and Innovation | Develop tailored talent development plans and learning and development offer those values and supports our staff through the transition and includes those training requirements outlined in the ICB training needs analysis | Corporate | Year 3 | Not yet started |
| Learning and Innovation | Design and deliver leading change programme to support managers and staff through change, transition and integration | Corporate | Year 1/2 | Complete |
| Learning and Innovation | Develop and embed innovation and continuous improvement tools and skills training | Corporate | Year 2/3 | In progress |
| Learning and Innovation | Review mandatory training requirements and reporting, monitoring processes following restructure | Corporate and Directorates | Year 2 | Complete |
| Learning and Innovation | Support staff to embrace digital and system change and transformation by designing and delivering training programmes that upskill staff in being able to maximise the benefits of new systems and processes | Directorate/ Service and team | Year 2/3 | In progress |
| Support, compassion and wellbeing | Introduce a just and restorative culture principles and approach to employee relations, incidents and complaints | Corporate | Year 3 | Not yet started |
| Support, compassion and wellbeing | Review communication channels and access to support staff to raise concerns | Corporate | Year 2 | Complete |
| Support, compassion and wellbeing | Establish access to a range of wellbeing initiatives that support people to stay well and healthy | Corporate and Directorates | Year 2/3 | In progress |
| Support, compassion and wellbeing | Support staff with change process with access to immediate health and wellbeing support | Corporate | Year 1/2 | Complete |
| Support, compassion and wellbeing | Develop and embed the role of the Wellbeing and Inclusion Guardian | Corporate | Year 1/2 | Complete |
| Support, compassion and wellbeing | Review and revise flexible and agile working practices and policy | Directorate/ Service and team | Year 2/3 | In progress |
| Support, compassion and wellbeing | Embed a civility and respect programme to promote a positive culture and tackle aggression, bullying, discrimination and harassment | Corporate | Year 3 | Not yet started |
| Support, compassion and wellbeing | Review and strengthen the role of exit interviews to continuously inform the OD Plan | Corporate/Directorates | Year 3 | Not yet started |
| Equity and Inclusion | Develop and deliver a programme to enable the ICB to be an anti-racist organisation and to tackle inequality | Corporate | Year 2/3 | In progress |
| Equity and Inclusion | Complete Equality Impact Assessment (EQIA) of new structure and management of change process and continue to embed approach to sustain best practice | Directorate/ Service and team | Year 1/2 | Complete |
| Equity and Inclusion | Develop and support staff networks to strengthen the employee voice in decision making, to change the ways things work and to create a more positive culture | Corporate and Directorate | Year 2/3 | In progress |
| Equity and Inclusion | Further promote and embed the NCL Workplace Adjustment Passport and guidance for managers | Corporate | Year 2/3 | In progress |
| Equity and Inclusion | Develop and implement plans to take positive action to address disparity in recruitment, career progression and employee relations cases (aligned to See Me First and A Fair Experience for All) | Corporate | Year 2/3 | In progress |
| Equity and Inclusion | Embed fair recruitment practices at all levels across the ICB | Directorate/ Service and teams | Year 2 | Complete |
| Team and system working | Deliver change and transition sessions with teams to support operational and personal resilience during change programme | Corporate | Year 1/2 | Complete |
| Team and system working | Develop and implement a high performing team development programme for the newly established teams | Corporate (with networks) | Year 2 | Complete |
| Team and system working | Develop a good practice guide for effective team communication, knowledge and information sharing | Corporate | Year 2/3 | In progress |
| Team and system working | Embed an approach to team development using proven methodology | Corporate | Year 2/3 | In progress |
| Team and system working | Design and embed a Board and Executive Team and senior leadership development programmes | Corporate | Year 2 | In progress |
| Team and system working | Complete an annual stakeholder/partner survey to gather feedback and inform system leadership development and continuous improvement | Corporate (with networks) | Year 3 | Not yet started |